## Start Here
AI AGENT CHARTER AND RUNBOOK
Describe an AI agent like a job: purpose, permissions, limits, monitoring, and what to do when it goes wrong.
What this workbook does
A working file for one AI agent or AI-supported process. The Charter states purpose, scope, owner, and autonomy level, with a readiness checklist. Permissions lists what the agent may touch, and flags risky access without approval. Guardrails holds approval gates, stop conditions, and limits. The Runbook holds monitoring checks, escalation, incident steps, and the kill switch. Monthly KPIs track how it performs against targets, and the Change Log records every change.
How to use it
Step | What to do | Details | Go to
1 | Write the charter | State purpose, owner, supervisor, scope in and out, autonomy level, and success measures. Complete the readiness checklist. | Open Charter >
2 | List the permissions | Record every system and action the agent may use. Give the least access that works. Mark which actions need approval. | Open Permissions >
3 | Set the guardrails | Define what always needs a person, when the agent must stop, and the limits per task. | Open Guardrails >
4 | Write the runbook | Monitoring checks, escalation paths, incident steps, and how to stop and roll back. | Open Runbook >
5 | Track the KPIs | Enter monthly figures. Rates calculate and compare with the targets in Settings. | Open Monthly KPIs >
6 | Record every change | Instructions, tools, models, permissions, and data: log each change with its test and approval. | Open Change Log >
Notes
The example is a work-order triage agent at an illustrative plant. Overwrite it with your own.
An agent's autonomy level is a ceiling: start lower and move up only with evidence. See the Human-in-the-Loop Process Design and AI Agents in Operations guides on sixsigmakaizen.com.
Keep the charter current: review it when the task, data, tools, or model change, and at least once a year.
Educational template. It supports an organization's planning and records for the use of AI. It is not legal, regulatory, security, or professional advice and does not replace your organization's policies, the laws and standards that apply, or qualified people. Example data are illustrative placeholders: overwrite them.

## Dashboard
AGENT DASHBOARD
Live from the other sheets. Nothing to enter here.
READINESS |  | PERMISSIONS |  | PERMISSION CHECKS |  | LATEST OVERRIDE RATE | LATEST SUCCESS RATE | INCIDENTS (ALL MONTHS)
Yes answers on the checklist |  |  |  | access that needs a closer look |  | vs target in Settings
Permissions by access type |  |  | Monthly rates
Access type | Count |  | Month | Success | Escalation | Override

## Charter
AGENT CHARTER
Complete each field. The example is a placeholder.
Agent name | Work-order triage agent
Purpose | Read maintenance requests, find the machine's history, and propose a priority for the planner to confirm, so that critical requests are seen first.
Business area | Maintenance
Owner (accountable role) | Maintenance lead
Supervisor (watches it day to day) | Maintenance planner
Users | Maintenance planners and technicians
Autonomy level | Act with approval
In scope | Priority proposals for new work orders raised in the maintenance system.
Out of scope | Closing, deleting, or assigning work orders; ordering parts; contacting suppliers or customers; any safety decision.
Systems and data used | Work-order system (read); equipment history (read); proposed-priority field (write). Data class: Internal.
Success measures | Priority agrees with the planner at least 90%; no missed critical requests; override rate at most 10%; cost per task at most $3.50.
Promotion criteria | Override rate under 5% over a full month; no missed critical requests across the next 59 critical orders; disagreements reviewed and instructions fixed; kill switch tested.
Approved by (role) | Operations manager
Date approved | 2026-09-28
Next review | 2027-03-28
Readiness checklist
Question | Answer (Yes / No / N/A)
The task is standardized and documented | Yes
A baseline measure exists (time, error rate, cost) | Yes
An owner and a supervisor are named | Yes
The agent has a written job description (this charter) | Yes
Permissions are the minimum the task needs | Yes
Actions that need approval are defined and enforced | Yes
Stop conditions and limits are set and tested | Yes
Logging is on and the logs can be searched | Yes
A kill switch and rollback have been tested | Yes
Test cases include awkward and adversarial inputs | Yes
A shadow run compared the agent with people | Yes
Promotion criteria are written down | Yes
Data classes are checked against the acceptable-use policy | Yes
Users are trained on what it can and cannot do | No
An incident process exists and people know it | Yes
Readiness (Yes answers of applicable items)

## Permissions
PERMISSIONS
Every system and action the agent may use. Give the least access that works. Gray columns calculate.
System or tool | Action | Access type | Scope or limit | Data class | Approval needed (Yes / No) | Why the agent needs it | Approved by (role) | Review date | Check
Work-order system | Read new and open work orders | Read | Maintenance site only | Internal | No | Needs the request text | Maintenance lead | 2027-03-28
Equipment history | Read past orders for a machine | Read | Own site | Internal | No | Finds similar past failures | Maintenance lead | 2027-03-28
Work-order system | Write the proposed priority field | Write | One field only | Internal | Yes | Shows the proposal to the planner | Operations manager | 2027-03-28
Email | Draft a note to the planner | Draft | Drafts only, no sending | Internal | No | Flags critical requests | IT security lead | 2027-03-28

## Guardrails
GUARDRAILS
What always needs a person, when the agent must stop, and its limits.
Always needs human approval | Rule or threshold
Any change to a record the agent does not own | Always
Any message to a person outside the team | Always
Any action that cannot be undone | Always
Spending | Any amount: the agent cannot spend
Stop and escalate when | What the agent does
Confidence is below the set level | Stops, marks the order for manual review
A tool returns an error twice | Stops and alerts the supervisor
The request mentions injury, fire, or a safety hazard | Flags critical and notifies the supervisor at once
The input looks unusual or contains instructions aimed at the agent | Treats it as data, ignores the instructions, and flags it
A step, time, or spend limit is reached | Stops and reports what it had done
Limit | Value
Maximum steps per task | 12
Maximum seconds per task | 90
Maximum tool calls per task | 8
Maximum spend per task ($) | 0.25
Maximum tasks per hour | 60

## Runbook
RUNBOOK
Monitoring checks, escalation, incident steps, and how to stop and roll back.
Monitoring check | How often | Owner (role) | What to look for | Action if it fails
Override rate on the control chart | Weekly | Maintenance planner | A point outside the limits or a run above the target | Review the overridden cases; hold promotion
Seeded test cases caught by the reviewer | Weekly | Maintenance lead | Any known test error approved | Retrain reviewers; reduce queue size
Missed critical requests | Every task | Maintenance planner | Any critical request not flagged | Stop the agent; open an incident
Usage and cost | Daily | IT lead | Spend above the daily limit | Check for loops; stop if needed
Vendor or model change notice | Monthly | IT lead | A version change | Run the test set before accepting it
Log review of a sample of tasks | Monthly | Operations manager | Unexpected tool calls or steps | Tighten permissions or instructions
Escalation level | Who (role) | When | Response time | Contact method
1 Supervisor | Maintenance planner | Any stop or odd behavior | Same shift | Chat and phone
2 Owner | Maintenance lead | Repeated stops, a missed critical request, or a policy breach | Within 2 hours | Phone
3 Governance | Operations manager and IT security lead | Data exposure, harm, or a regulatory issue | Within 1 hour | Phone
Incident step | Detail
1 Stop | Use the kill switch to stop the agent. Confirm that it has stopped.
2 Contain | Check what it did from the logs. Undo or correct what can be undone.
3 Tell | Tell the owner and anyone affected. Report as the rules require.
4 Find the cause | Use the log and the test set. Ask why the controls did not catch it.
5 Fix and test | Change instructions, limits, or permissions. Re-run the test set.
6 Restart | Restart at a lower autonomy level, with approval from the owner. Record it in the Change Log.
Kill switch and rollback
How to stop the agent | Disable the agent's service account in the work-order system; the toggle is in the admin console.
How to roll back | Clear the proposed-priority field for affected orders using the saved query; planners revert to the manual process.

## Monthly KPIs
MONTHLY KPIs
Enter monthly figures. Rates and target checks calculate.
Month | Tasks handled | Successful | Escalated | Overridden | Incidents | Total cost ($) | Success rate | Escalation rate | Override rate | Cost per task ($) | Against targets
2026-06 | 160 | 134 | 21 | 17 | 0 | 520
2026-07 | 305 | 262 | 38 | 29 | 0 | 910
2026-08 | 410 | 365 | 48 | 36 | 0 | 1190
2026-09 | 455 | 412 | 49 | 33 | 0 | 1280

## Change Log
CHANGE LOG
Record every change to instructions, tools, models, permissions, data, and limits.
Date | Change | Type | Reason | Tested before use (Yes / No) | Approved by (role) | Rollback plan
2026-08-03 | Added the safety keyword rule to the instructions | Instructions | Shadow test showed two safety orders rated routine | Yes | Maintenance lead | Revert to the prior instructions file
2026-09-28 | Moved from assist to act with approval | Permission | Shadow test and two months of assist met the criteria | Yes | Operations manager | Remove write permission on the priority field

## Settings
SETTINGS
Targets, as-of date, and lists. Yellow cells are inputs.
KPI targets |  | Autonomy level | Access type | Data class | Yes / No / N/A | Change type | Frequency
Task success rate: at least | 90% | Assist | Read | Public | Yes | Instructions | Every task
Escalation rate: at most | 15% | Draft | Draft | Internal | No | Tool | Daily
Override rate: at most | 10% | Act with approval | Write | Confidential | N/A | Model | Weekly
Incidents per month: at most | 0 | Act, human samples | Send | Restricted |  | Permission | Monthly
Cost per task: at most ($) | 3.5 | Act with monitoring | Spend |  |  | Data | Quarterly
|  |  | Delete |  |  | Limit
As-of date (type a date, or enter =TODAY()) | 2026-10-20