## Start Here
AI RISK REGISTER (FMEA FOR AI)
List what can go wrong with each AI use, rate it, choose controls, and track the actions.
What this workbook does
A failure mode and effects analysis for AI uses. For each failure mode you rate severity, occurrence, and detection from 1 to 10 before and after controls. The risk priority number (RPN) and its band calculate, and any severity at or above the flag level is marked for review whatever its RPN. The Dashboard shows the bands before and after, the top residual risks, and overdue actions.
How to use it
Step | What to do | Details | Go to
1 | Set the scales | Read and edit the severity, occurrence, and detection scales, the RPN bands, and the lists. | Open Settings >
2 | Pick failure modes | Use the library of common AI failure modes as a starting point, and add your own. | Open Settings >
3 | Rate the risks | For each AI use, enter the failure mode, effect, cause, and existing controls, and rate S, O, and D. | Open Register >
4 | Choose controls | Record the action, its type, owner, and due date. Re-rate S, O, and D as they would be with the control in place. | Open Register >
5 | Track actions | Update status and the date done. Overdue actions flag against the as-of date. | Open Register >
6 | Review the dashboard | See the risks by band before and after, the top residual risks, and the overdue actions. | Open Dashboard >
Notes
RPN has known limits. Treat severity first: a high-severity failure needs action whatever its RPN. The flag column does this.
Rate the failure as the process runs today, with existing controls, before adding new ones.
See the AI Governance and Risk for Operations guide and the FMEA guide on sixsigmakaizen.com.
Educational template. It supports an organization's planning and records for the use of AI. It is not legal, regulatory, security, or professional advice and does not replace your organization's policies, the laws and standards that apply, or qualified people. Example data are illustrative placeholders: overwrite them.

## Dashboard
AI RISK DASHBOARD
Live from the Register. Nothing to enter here.
RISKS RATED |  | HIGH BEFORE |  | HIGH AFTER | AVERAGE RPN REDUCTION | SEVERITY FLAGS | ACTIONS OVERDUE
Risks by band
Band | Before | After
High
Medium
Low
Top five residual risks
Rank | Failure mode | RPN after | Band after | Owner
1
2
3
4
5
Actions by control type
Control type | Actions

## Register
AI RISK REGISTER
Rate S, O, and D from 1 to 10 using the Settings scales. Yellow cells are inputs; gray cells calculate. Example rows are placeholders.
ID | AI use or system | Failure mode | Effect | Cause | Existing controls | S | O | D | RPN | Band | Review flag | Recommended action | Control type | Owner | Due date | Status | Date done | S after | O after | D after | RPN after | Band after | Overdue | Rank
R-01 | Complaint triage | Safety complaint classified as routine | A safety complaint reaches the wrong team late | No rule for safety wording; low-confidence items not reviewed | Weekly manual spot check | 9 | 4 | 6 |  |  |  | Keyword safety rule, plus human review of low-confidence items | Detection or check | Customer service lead | 2026-11-15 | In progress |  | 9 | 2 | 3
R-02 | Reply drafting | Drafted reply cites a part number that does not exist | A wrong reply goes to a customer | The model invents details | Reviewer reads the draft | 6 | 5 | 5 |  |  |  | Look-up check of every part number against the catalog before sending | Detection or check | Customer service lead | 2026-10-01 | Done | 2026-10-01 | 6 | 3 | 2
R-03 | All users | Confidential customer data pasted into a public AI tool | Customer data is exposed | Staff paste data into public tools | A policy exists, not enforced | 8 | 5 | 7 |  |  |  | Approved tools only, data classification rules, and training | Policy or training | IT security lead | 2026-11-30 | In progress |  | 8 | 2 | 3
R-04 | Maintenance agent | Agent closes a work order that is not finished | Equipment is left unserviced | The agent trusts the ticket status | Planner reviews daily | 7 | 3 | 7 |  |  |  | Closure needs a technician confirmation step and a photo | Design or process | Maintenance lead | 2026-10-10 | Open |  | 7 | 2 | 3
R-05 | Complaint intake | Instructions hidden in a customer email change agent behavior | The agent takes actions it should not | Text in an email is read as an instruction | None | 8 | 3 | 8 |  |  |  | Treat email text as data, restrict agent tools, and filter outputs | Design or process | IT security lead | 2026-12-15 | Open |  | 8 | 2 | 4
R-06 | All systems | Vendor model update changes behavior without notice | Results change without anyone noticing | The vendor updates the model | None | 6 | 4 | 8 |  |  |  | Pin the version; re-run the test set before changing | Vendor or contract | Operations manager | 2026-10-15 | Done | 2026-10-15 | 6 | 3 | 3
R-07 | Human review | Reviewers approve outputs without checking | Errors reach customers or records | Reviewers approve in bulk | Sign-off by the reviewer | 7 | 6 | 7 |  |  |  | Seed known errors into the queue; rotate reviewers; track the catch rate | Human review | Quality manager | 2026-12-01 | Open |  | 7 | 4 | 4
R-08 | Maintenance agent | Agent loops and runs up usage cost | Usage costs rise sharply | The agent repeats steps without a limit | None | 4 | 3 | 4 |  |  |  | Step and spend limits per task, with an alert | Design or process | Maintenance lead | 2026-10-05 | Done | 2026-10-05 | 4 | 2 | 2

## Settings
SETTINGS
Scales, bands, and lists. Yellow cells are inputs; the Register and Dashboard read from here.
Score | Severity: effect of the failure | Occurrence: how often it could happen | Detection: chance we catch it first | Control type | Status | Failure mode library (common AI failure modes)
1 | No real effect | Almost never | Almost certain to be caught before use | Design or process | Open | Wrong output stated confidently
2 | Minor annoyance | Very rare | Very likely caught | Detection or check | In progress | Misclassification
3 | Small rework | Rare | Likely caught | Human review | Done | Data leakage
4 | Noticeable delay or cost | Occasional | Fairly likely caught | Policy or training | Verified | Manipulated input (prompt injection)
5 | Customer or cost impact | Sometimes | Moderate chance caught | Vendor or contract |  | Drift or silent vendor change
6 | Significant cost or customer complaint | Fairly often | Less than even chance |  |  | Over-reliance by reviewers
7 | Major cost, safety near miss, or compliance finding | Often | Unlikely caught |  |  | Bias or unequal error rates
8 | Serious harm risk or regulatory breach | Frequent | Very unlikely caught |  |  | Runaway action or cost
9 | Severe harm, serious legal or regulatory breach | Very frequent | Almost never caught |  |  | Unavailable or slow service
10 | Fatality or catastrophic, widespread harm | Almost certain | No control; cannot be detected |  |  | Missing or wrong source data
Output used outside its scope
Loss of skills or knowledge
RPN bands, severity flag, and as-of date
200 | High: RPN at or above
100 | Medium: RPN at or above
9 | Flag any severity at or above
2026-10-20 | As-of date (type a date, or enter =TODAY())