## Start Here
AI WORKFORCE IMPACT AND TRAINING PLAN
Plan how AI changes tasks and roles, who needs which training, and how you involve the people affected.
What this workbook does
A workbook for the people side of an AI use. The Task Changes sheet lists the tasks of each affected role with hours per week before and after AI, and how AI is involved. The Roles sheet adds them up by role and shows the time now spent checking AI output and handling exceptions, and the first-pass work removed. The Training Plan sheet tracks who needs which training and who has had it. The Engagement log records briefings, feedback, concerns, and what you did about them. The Dashboard summarizes progress.
How to use it
Step | What to do | Details | Go to
1 | Name the roles | List the roles whose work changes and the number of people in each. | Open Roles >
2 | Map the task changes | With the people who do the work, list each task and the hours per week before and after, and how AI is involved. The hours for a role should add up to the same total. | Open Task Changes >
3 | Plan the training | List the audiences and topics, the method, the number to train, the owner, and the due date. | Open Training Plan >
4 | Record the engagement | Log each briefing, workshop, survey, or conversation, the concern raised, and the response. | Open Engagement >
5 | Check the dashboard | See the checking workload, training completion, and open concerns. Review at 30, 90, and 180 days. | Open Dashboard >
Notes
Say plainly what the AI is not for and what will happen to the time it frees, and keep the promise.
Do not use AI to monitor, score, or rank workers without a clear purpose, a policy, and legal and HR review. Rules vary by place. This workbook is not legal or HR advice.
See the Workforce and Change for AI guide on sixsigmakaizen.com.
Educational template. It supports an organization's planning and records for the use of AI. It is not legal, regulatory, security, or professional advice and does not replace your organization's policies, the laws and standards that apply, or qualified people. Example data are illustrative placeholders: overwrite them.

## Dashboard
WORKFORCE DASHBOARD
Live from the other sheets. Nothing to enter here.
ROLES AFFECTED |  | PEOPLE AFFECTED |  | HOURS CHECKING PER WEEK |  | TRAINED | TRAINING OVERDUE | OPEN CONCERNS
|  |  |  | whole team, checking and exceptions |  | of people to train |  | not yet closed
Hours per person per week, by role |  |  |  |  | Training by status
Role | Before | After | Checking or exceptions |  | Status | Items
Done
In progress
Overdue

## Task Changes
TASK CHANGES
One row per task per role. Hours are per person per week. Gray columns calculate. Examples are placeholders: overwrite them.
Role | Task | Hours per week before | Hours per week after | Change | How AI is involved | Notes
Complaint analyst | Reading and coding complaints | 14 | 3 |  | AI does first pass
Complaint analyst | Checking AI coding and handling exceptions | 0 | 9 |  | Person checks AI output
Complaint analyst | Drafting replies | 10 | 4 |  | AI assists
Complaint analyst | Investigating causes | 8 | 12 |  | None
Complaint analyst | Admin and meetings | 6 | 5 |  | None
Complaint analyst | Improvement work | 2 | 7 |  | None
Maintenance planner | Triage of new work orders | 12 | 4 |  | AI does first pass
Maintenance planner | Checking AI triage | 0 | 5 |  | Person checks AI output
Maintenance planner | Scheduling | 14 | 14 |  | None
Maintenance planner | Parts and permits | 8 | 8 |  | None
Maintenance planner | Meetings | 6 | 5 |  | None
Maintenance planner | Improvement work | 0 | 4 |  | None
Customer service lead | Team coaching | 12 | 12 |  | None
Customer service lead | Escalations | 14 | 12 |  | Person handles exceptions
Customer service lead | Reporting | 8 | 5 |  | AI assists
Customer service lead | Reviewing AI-drafted replies | 6 | 8 |  | Person checks AI output
Customer service lead | Improvement work | 0 | 3 |  | None

## Roles
ROLES
One row per role. Gray columns add up the Task Changes sheet. Examples are placeholders.
Role | People in the role | Hours before (per person) | Hours after (per person) | Hours check | Hours checking or handling exceptions | Share of week on checking | First-pass hours before | First-pass hours after | Hours freed (per person) | Team hours freed per week
Complaint analyst | 6
Maintenance planner | 4
Customer service lead | 2

## Training Plan
TRAINING PLAN
One row per audience and topic. Gray columns calculate. Examples are placeholders: overwrite them.
Audience | Topic | Method | People to train | People trained | Percent trained | Owner (role) | Due date | Status
All staff who use AI | What the tools do and get wrong | Workshop | 120 | 96 |  | Training lead | 2026-09-30
All staff who use AI | Data rules: what may go into which tool | Online course | 120 | 118 |  | Privacy lead | 2026-09-30
All staff who use AI | Spotting hidden instructions in documents and messages | Toolbox talk | 120 | 60 |  | Security lead | 2026-10-31
Reviewers | Checking AI output against the source; seeded-error practice | Workshop | 14 | 14 |  | Quality lead | 2026-09-15
Use owners | Reading the monitoring chart; deciding to pause or retire | Workshop | 6 | 4 |  | Governance lead | 2026-10-15
Prompt and data stewards | Writing and testing prompts; golden sets | Workshop | 4 | 4 |  | Quality lead | 2026-09-30
AI champions | Helping peers; collecting questions | Coaching | 8 | 5 |  | Training lead | 2026-11-30
Supervisors | Talking with the team about AI changes | Workshop | 12 | 7 |  | HR partner | 2026-10-10

## Engagement
ENGAGEMENT LOG
One row per briefing, workshop, survey, or conversation. Record what was raised and what you did. Examples are placeholders.
Date | Group | Activity | Concern or question raised | Response or change made | Owner (role) | Status | Due | Check
2026-08-17 | Complaint analysts | Briefing | Will this replace us? | Leaders stated in writing that freed time goes to investigation and improvement work, and that no one loses a role because of this use | Operations manager | Closed | 2026-08-31
2026-08-24 | Complaint analysts | Workshop | The tool miscodes cases about two product lines | Added those cases to the test set and to the checking rule | Quality lead | Closed | 2026-09-14
2026-09-14 | Maintenance planners | Pilot feedback | Reviewing triage takes longer on busy days | Moved the review to the start of shift and capped the daily queue | Planning lead | Closed | 2026-09-30
2026-09-28 | Customer service team | Survey | Some people are unsure when they may override the AI | Write a one-page rule on overriding; add to the training | Customer service lead | Open | 2026-10-12
2026-10-07 | Supervisors | 1:1 | How will AI results be used in performance reviews? | Draft a statement: the AI tool is not used to score individuals; confirm with HR and legal | HR partner | Open | 2026-10-30

## Settings
SETTINGS
As-of date and lists. Yellow cells are inputs.
|  | AI involvement | Training method | Activity | Status
As-of date (type a date, or enter =TODAY()) | 2026-10-21 | None | Workshop | Briefing | Open
|  | AI does first pass | Online course | Workshop | Closed
|  | AI assists | Toolbox talk | Survey
|  | Person checks AI output | Coaching | Pilot feedback
|  | Person handles exceptions | On the job | 1:1
Other